## Tracking
COLLECTION | BOX ID | STATUS | ASSIGNED TO/COMPLETED BY | LOCATION OF PHYSICAL BOX | LOCATION OF DIGITAL FILES | QUALITY CHECK | TURNED INTO DOJ?
Reed Marbut |  |  |  |  | https://stateoforegon.sharepoint.com/:f:/r/sites/OWRD/AS/Shared%20Documents/Support%20Services/Records%20Management/Working%20folder/KLAMATH/MARBUT?csf=1&web=1&e=Aa2iFO
| RM Box 1 | scanning complete | JW | Law Library | https://stateoforegon.sharepoint.com/:x:/r/sites/OWRD/AS/Shared%20Documents/Support%20Services/Records%20Management/Working%20folder/KLAMATH/MARBUT/Box%201/RM%20Box%201.xlsx?d=w2a29fa3e58d94d6590f412539377126b&csf=1&web=1&e=dLqHbB | complete | YES
| RM Box 2 | scanning complete | CL | Front desk |  |  | NO
| RM Box 3 | scanning complete | NR | Front desk |  |  | NO
| RM Box 4 | in progress | NR | Front desk |  |  | NO
Martha Pagel
| MOP Box 1 | scanning complete | MC | Law library | https://stateoforegon.sharepoint.com/:x:/r/sites/OWRD/AS/Shared%20Documents/Support%20Services/Records%20Management/DOJ/Sprague%20river/PAGEL/Pagel%20Klamath%20Files.xlsx?d=w68a863b3ecf7455e83077f59f4bbcbe8&csf=1&web=1&e=llAQAW | complete | YES
| MOP Box 2 | scanning complete | MC | Law library | https://stateoforegon.sharepoint.com/:x:/r/sites/OWRD/AS/Shared%20Documents/Support%20Services/Records%20Management/DOJ/Sprague%20river/PAGEL/Pagel%20Klamath%20Files.xlsx?d=w68a863b3ecf7455e83077f59f4bbcbe8&csf=1&web=1&e=llAQAW | complete | YES
Tom Byler
| TB Box 1 | scanning complete | MC | Law library |  | needs IDs | NO
Phil Ward |  |  |  |  | https://stateoforegon.sharepoint.com/:f:/r/sites/OWRD/AS/Shared%20Documents/Support%20Services/Records%20Management/Working%20folder/KLAMATH/WARD?csf=1&web=1&e=Iqkb3K
| PW Box 1 | scanning complete | JW | Law Library | https://stateoforegon.sharepoint.com/:x:/r/sites/OWRD/AS/Shared%20Documents/Support%20Services/Records%20Management/Working%20folder/KLAMATH/WARD/PW%20Box%201.xlsx?d=w2f56a98c765f48b3bf3ba1cb59bb8d14&csf=1&web=1&e=wVIpOK | complete | YES
KL Reference |  |  |  |  | https://stateoforegon.sharepoint.com/:f:/r/sites/OWRD/AS/Shared%20Documents/Support%20Services/Records%20Management/Working%20folder/KLAMATH/1stFloor/KL%20Box%201?csf=1&web=1&e=CQLgXb
| KL Box 1 | scanning complete | NR | Front desk | https://stateoforegon.sharepoint.com/:f:/r/sites/OWRD/AS/Shared%20Documents/Support%20Services/Records%20Management/Working%20folder/KLAMATH/1stFloor/KL%20Box%201?csf=1&web=1&e=b6TEUr | complete | YES
| KL Box 2 | scanning complete | NR | Front desk | KL Box 2 |  | YES
| KL Box 3 | scanning complete | NR | Front desk | KL Box 3 |  | YES
| KL Box 4 | scanning complete | CL | Front desk | KL Box 4 | need to fix file name error in spreadsheet and move desk manuals to their own box | NO
| KL Box 5 | scanning complete | NR/CL | Front desk | adair |  | NO
| KL Box 6 | scanning complete | NR/CL | Front desk |  |  | NO
| KL Box 7 | scanning complete | JW | Rogue | KRCC materials from "historical stash" DO |  | YES
| KL Box 8 | scanning complete | NR/CL | Front desk |  | NEEDS REVIEW
| KL Box 9 | scanning complete | NR/CL | Front desk |  | NEEDS REVIEW
| KL Box 10 | scanning complete | NR/CL | Front desk |  | NEEDS REVIEW
| KL Box 11 | not started |  | WR cabinets
| KLBox 12 | not started |  | WR cabinets
Klamath Adjudication Staff Records |  |  |  |  | https://stateoforegon.sharepoint.com/:f:/r/sites/OWRD/AS/Shared%20Documents/Support%20Services/Records%20Management/Working%20folder/KLAMATH/1stFloor/KAS%20Box%201?csf=1&web=1&e=SCerUS
| KAS Box 1 | scanning complete | CL | Front desk | https://stateoforegon.sharepoint.com/:x:/r/sites/OWRD/AS/Shared%20Documents/Support%20Services/Records%20Management/Working%20folder/KLAMATH/1stFloor/KAS%20Box%201/KAS%20Box%201.xlsx?d=w287c660ef7f4475687e53779f340b856&csf=1&web=1&e=vDU2dA | complete | YES
| KAS Box 2 | scanning complete | CL | Front desk | https://stateoforegon.sharepoint.com/:f:/s/OWRD/AS/ErIriOFF26VPn1MNpS7FjxoBfP3TaXdZP4Zrvqy2GYLBOA?e=0r7asp |  | YES
| KAS Box 3 | scanning complete | CL | Front desk |  |  | YES
| KAS Box 4 | scanning complete | MC | MC |  |  | NO
| KAS Box 5 | scanning complete |  | WR cabinets |  | MARK FOR REDACTION | NO
| KAS Box 6 | scanning in progress | MC | MC | Geisen box |  | NO
| KAS Box 7 | scanning complete with exceptions | MC | Rogue | "ADR Meeting records", sveral tapes to be converted |  | NO
| KAS Box 8 | not started |  | WR cabinets |  |  | NO
| KAS Box 9 | not started |  | WR cabinets |  |  | NO
Klamath Adjudication Staff Records
| KFFS Box 1 | scanning in progress | CL
| KFFS Box 2 | not started
| KFFS Box 3 | not started

## Vault records map
VAULT Row H | VAULT Maps
Book 1-9 (~2.5 boxes) | at least 7 drawers of maps
Book 10-13; NOI 1-6 (~2.5 boxes)
NOI 7-10 + 2 small boxes (~2 boxes)
X
KBA FFOD (~3 boxes)
KBA OAH Hearing Tapes and DVDs
Maps (~1 box)

## WR FC-1-21-29
| FC-1-21 | FC-1-22 | FC-1-23 | FC-1-24 | FC-1-25 | FC-1-26 | FC-1-27 | FC-1-28 | FC-1-29
drawer 1 | X | ? (lost river all 5 d) | ? | KAC 1 | KAC 6 | KL 1 | KAS 1 | KAC 9 | KAC 14
drawer 2 | KAC 9 | ? | ? | KAC 2 | KAC 7 | KAC 8 | KAS 2 | KAC 10 | KAC 15 | 18 | KAC | Klamath Adj Claims
drawer 3 | X | ? | Fragile 1 | KAC 3 | KL 4 | KL 2 | KAS 3 | KAC 11 | KAC 16 | 5 | KAS | Klamath Adj Staff Records
drawer 4 | X | ? | Fragile 2 | KAC 4 | KL 5 | ? Water for life | KAS 4 | KAC 12 | KAC 17 | 6 | KL | Klamath Reference Materials
drawer 5 | ? | ? | Fragile 3 | KAC 5 | KL 6 | KL 3 | KAS 5 | KAC 13 | KAC 18 | 3 | Fragile | Fragile 1909 claims
[10 empty] | 32 | total
[10 empty] | 9 | ? | need Sara's input
[10 empty] | 3 | X | empty or unrelated